## Sheet1
Screen/area | Task | Estimate, days | Status
Alert screen | Implement GUI elements | 3 | Done
| Add functions for buttons | 0.5
| Create queries and AJAX calls | 0.5
| Add dummy data to database | 0.5
| Reformat query response JSON | 0.5
| Integrate D3 graph | 0.5
| Add deep link popup | 0.25
Connectivity Screen | Implement GUI elements
Add functions for buttons
Create queries and AJAX calls
Add dummy data to database
Integrate D3 graph
Best Practices screen | GUI elements
Button functions
Queries and Ajax calls
Database data
D3 graph
Main screen | GUI elements |  |  | f
Link functions with URLs to server
Create query and AJAX calls
Reformat query response JSON
Integrate D3 graph
Status and problems screen | TBD
Operations screen | TBD
Deep links | Database: Add links as properties to some database elements | 0.25
| GUI: add deeplink dummy popup screen | 0.5 | Done
Database | Clean up relationships to all follow "depends on" direction | 0.5
| Set relationships as transitive or intransitive | 0.5
D3 graphs | Nodes: distinguish by shape and color | 0.25 | Done
| Nodes: add status icons | 0.5 | Done
| Nodes: add property view window that can contain deep link URLs | 0.5 | Done
Piano graphs | Add client-side function to convert database JSON to Piano control format
Replicate all D3 functions in Piano format
Integrate Piano graphs into existing screens
Graph | Set shapes and colors of nodes | 1 | Done
| Set labels on nodes | 0.1 | Done
| Add icons to nodes | 0.5 | Done
| Add property window that follows currently selected node | 0.5 | Done
| Zoom | 0.25 | Done
| Reposition | 0.25 | Done
| Change scope: add/remove hops from central node to edge nodes | 0.5 | Done
| Set color and width of edges | ??
| Set labels on edges |  | Deferred
Server | Set up web server with containing screen pages and js libs. - Unless we do it all on files from a local machine
Database | Add large scale sets of objects
Create a script file to build the database in one step
Reasearch | Cinder Data acccess: initial data, determine what is currently available without changing existing code
Cinder Data acccess: model updates. Look at how data can be updated without changing existing code: log files message queue device manager notifications Monasca notifications
Alternate D3 layouts Hierarchical Edge Bundling Reingold-Tilford Trees